BA-PHALABORWA MUNICIPALITY

2014/15 INSTITUTIONAL SDBIP

The Home of Marula and Wildlife Tourism

TABLE OF CONTENTS

Introduction 											3

Legislation 											4

Methodology and Content 									5

Strategic Intent 			 								6

Monthly Projections of Revenue for each Source							8

Monthly Projections of Revenue and Expenditure by Vote: 1st Quarter 				9

Monthly Projections of Revenue and Expenditure by Vote: 2nd Quarter				10

Monthly Projections of Revenue and Expenditure by Vote: 3rd Quarter				11

Monthly Projections of Revenue and Expenditure by Vote: 4th Quarter				12

Total Monthly projections of revenue and Expenditure by Vote for 2014/15			13

Quarterly projections of Service Delivery Targets and Performance Indicators per KPA		14

KPA 1: Municipal Transformation and Institutional Development 				            14

KPA 2: Basic Service Delivery 									18

KPA 3: Local Economic Development 								23

KPA 4: Municipal Financial Viability and Management 						26

KPA 5: Good Governance and Public Participation						31

Capital Works Plan 									38

Summary of Capital Projects per Responsible Manager 						38

SDBIP Approval 								         44-46

# Introduction

The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is a requirement of the Municipal Finance Management Act, Act 56 0f 2003. The SDBIP gives effect to the Integrated Development Plan (IDP) and Budget of a Municipality and will be possible if the Budget is aligned to the IDP. The SDBIP is a management plan for implementing the IDP through the approved Budget.

The SDBIP is a twelve months implementation plan that binds the executive and administration to align their activities to the strategic objectives of the institution. It provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly revenue and expenditure projections. It assists the accounting officer, the executive, council and the community in their respective oversight responsibilities, since it serves as an implementation and monitoring tool.

In the interest of good governance and better accountability, the SDBIP should determine and be aligned with the performance agreements of the Municipal Manager and Senior Managers. The SDBIP is, therefore,, defined as an action plan with revenue projections, expenditure estimates and allocations of resources to priority issues. The SDBIP has targets for the implementation of projects and/or activities. Monthly, quarterly, half-yearly and annual targets with allocated resources and responsible persons are clearly set in the SDBIP.

# Legislation

Section 1 of the MFMA defines the SDBIP as:

“a detailed plan approved by the mayor of a municipality in terms of section 53(1)(c)(ii) for implementing the municipality’s delivery of services and the execution of its annual budget and which must include (as part of the top-layer) the following:

(a) projections for each month of-

(i) revenue to be collected, by source; and

(ii) operational and capital expenditure, by vote;

(b) service delivery targets and performance indicators for each quarter”

Section 69(3)(a) of the MFMA requires the accounting officer to submit a draft SDBIP to the mayor no later than 14 days after the approval of the budget and drafts of the performance agreements as required in terms of Section 57(1)(b) of the Municipal Systems Act.

Section 53 (1) (c) (ii) requires that a municipality’s Service Delivery and Budget Implementation Plan be approved by the Mayor within 28 days after the approval of the budget. Although the SDBIP is not required to be approved by council, it should be tabled before council and made public for information and for purposes of monitoring.

Despite the legislated deadlines, MFMA Circular No. 13 states that “[a] municipality should ideally publish its draft SDBIP with its draft budget as supporting documentation to assist its budget hearing process normally held at the end of March or in April.” In order for a municipality to comply with the provisions of this statement, the mayor will need to approve the draft top-layer SDBIP by mid-March.

The Mayor must also ensure that the revenue and expenditure projections for each month and the service delivery targets and performance indicators as set out in the SDBIP are made public within 14 days after approval. The SDBIP is a dynamic document that may (at lower layers of the plan) be continually revised by the municipal manager and other top managers, as actual performance after each month or quarter is taken into account. However, the top-layer of the SDBIP and its targets cannot be revised without notifying the council, and if there is to be changes in service delivery targets and performance indicators, this must be with the approval of the council, following approval of an adjustments budget (Section 54(1)(c) of MFMA). The contemplated council approval is meant to avoid a situation where service delivery targets may be revised downwards in the event that there is poor performance.

# Methodology and Content

The IDP objectives need to be quantified and translated into key performance indicators. The budget is then aligned to the objectives, projects and activities to enable the SDBIP to serve as a monitoring tool for service delivery.

The SDBIP is a layered plan that comprises the top layer as well as the lower layer SDBIP. The top layer deals with consolidated service delivery targets and time frames for top management, whereas the lower layer consists of detailed outputs that are broken down into smaller outputs and then linked and assigned to middle and lower managers.

The following are the minimum required components of a top-layer SDBIP:

(a) Monthly projections of revenue to be collected for each source

(b) Monthly projections of expenditure (operating and capital) and revenue for each vote

(c) Quarterly projections of service delivery targets and performance indicators for each vote

(d) Ward information for expenditure and service delivery

(e) Detailed capital works plan broken down by ward over three years

The diagram below shows the process for approving the SDBIP including how the departmental SDBIPs roll up into the draft SDBIP:

Draft Budget with proposed annual measurable performance indicators and projections for outer two years

Strategic direction and priorities set by Council

Draft Departmental SDBIPs with proposed monthly and quarterly projections for the 1st year and annual projections for the two outer years rolled up into the draft SDBIP

Approved Budget

Department 2

Department 3

SDBIP

Approved SDBIP with monthly projections for revenue and expenditure and quarterly projections for service delivery targets and performance indicators

Approved annual performance agreements for municipal manager and senior managers

Municipal Budget Policy Statement with indicative allocations for Revenue and Expenditure including initial tariff modelling etc. (prepared by the municipal Budget & Treasury Office)

Draft SDBIP

Diagram adapted from MFMA Circular No. 13 of 31 January 2005

# Strategic Intent

The Municipality held a strategic session between the 02nd December and 5th December 2013 to review its strategic intent as follows:

Vision:

“Provision of quality services for community well-being and tourism development”

Mission Statement:

“To provide quality infrastructure and affordable services, promote sustainable economic growth, financial viability, sound administration and accountable governance”.

Values:

“Efficiency and effectiveness;

Accountability;

Innovation and creativity;

Professionalism and hospitality;

Transparency and fairness;

Continuous learning; and

Conservation conscious”.

Strategic Objectives:

“Promotion of Local economy;

Provision of sustainable integrated infrastructure and services;

Sustain the environment;

Improve financial viability;

Good corporate governance and public participation; and

Attract, develop and retain best human capital”.

The Municipality has adopted a Balanced Scorecard approach to planning and performance assessment. The strategic objectives are therefore spread across the four perspectives as indicated through the strategy map below:

“PROVISION OF DEVELOPMENT QUALITY SERVICES FOR COMMUNITY WELL-BEING AND TOURISM “

THE HOME OF MARULA WILDLIFE TOURISM

STRATEGIC PERSPECTIVE

Learning and Growth           Institutional Processes                Finances                       Community Satisfaction

Provision of sustainable integrated infrastructure and services

Promotion of Local Economy

Improve financial viability

Sustain the environment

Good corporate governance and public participation

Attract, develop and retain best human capital

# Monthly Projections of Revenue for Each Source

| Sources of Revenue | 2014 Monthly Projections R’000 |  |  |  |  |  | 2015 Monthly Projections R’000 |  |  |  |  |  | Total | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jul. | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May | June |  |  |
| Property Rates | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 5,886 | 70,634 | Billing VS Collection |
| Service charges – electricity | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 7,944 | 95,327 | Billing VS Collection |
| Service Charges – Refuse | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 945 | 11,337 | Billing VS Collection |
| Rental of Facilities and Equipment | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 330 | Billing VS Collection |
| Interest on external Investments | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 260 | Billing VS Collection |
| Interest Earned – Outstanding Debtors | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 6,220 | 74,644 | Billing VS Collection |
| Dividends received | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | Billing VS Collection |
| Fines | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 217 | 2,600 | Billing VS Collection |
| Licenses and Permits | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 9,021 | Billing VS Collection |
| Agency services | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 2,255 | Billing VS Collection |
| Transfers recognised - operational | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 7,374 | 88,490 | Billing VS Collection |
| Transfers recognised - capital | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 3,107 | 37,279 | Billing VS Collection |
| Other Revenue | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1,352 | Billing VS Collection |
| Total Revenue by Source | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 32,794 | 393,530 |  |

Monthly Projections of Expenditure (Operating and Capital) and Revenue by Vote: First Quarter

| Expenditure and Revenue by Vote | July 2014 |  |  | August 2014 |  |  | September 2014 |  |  | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev |  |
| Executive and council | 3,042 | 0 | 0 | 3,042 | 0 | 0 | 3,042 | 0 | 0 | Financial Reports |
| Budget and Treasury | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | Financial Reports |
| Corporate Services | 3,519 | 375 | 28 | 3,519 | 375 | 28 | 3,519 | 375 | 28 | Financial Reports |
| Community and Social Services | 3,851 | 83 | 964 | 3,851 | 83 | 964 | 3,851 | 83 | 964 | Financial Reports |
| Public Safety | 1,005 | 50 | 218 | 1,005 | 50 | 218 | 1,005 | 50 | 218 | Financial Reports |
| Economic and Environmental Services | 1,425 | 0 | 0 | 1,425 | 0 | 0 | 1,425 | 0 | 0 | Financial Reports |
| Road Transport | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | Financial Reports |
| Electricity | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | Financial Reports |
| Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Water Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Management | 450 | 0 | 945 | 450 | 0 | 945 | 450 | 0 | 945 | Financial Reports |
| Total by Vote | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 |  |

Monthly Projections of Revenue and Expenditure by Vote: Second Quarter

| Expenditure and Revenue by Vote | October 2014 |  |  | November 2014 |  |  | December 2014 |  |  | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev |  |
| Executive and council | 3,042 | 0 | 0 | 3,042 | 0 | 0 | 3,042 | 0 | 0 | Financial reports |
| Budget and Treasury | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | Financial reports |
| Corporate Services | 3,519 | 375 | 28 | 3,519 | 375 | 28 | 3,519 | 375 | 28 | Financial reports |
| Community and Social Services | 3,851 | 83 | 964 | 3,851 | 83 | 964 | 3,851 | 83 | 964 | Financial reports |
| Public Safety | 1,005 | 50 | 218 | 1,005 | 50 | 218 | 1,005 | 50 | 218 | Financial reports |
| Economic and Environmental Services | 1,425 | 0 | 0 | 1,425 | 0 | 0 | 1,425 | 0 | 0 | Financial reports |
| Road Transport | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | Financial reports |
| Electricity | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | Financial reports |
| Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial reports |
| Waste Water Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial reports |
| Waste Management | 450 | 0 | 945 | 450 | 0 | 945 | 450 | 0 | 945 | Financial reports |
| Total by Vote | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 |  |

Monthly Projections of Revenue and Expenditure by Vote: Third Quarter

| Expenditure and Revenue by Vote | January 2015 |  |  | February 2015 |  |  | March 2015 |  |  | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev |  |
| Executive and council | 3,042 | 0 | 0 | 3,042 | 0 | 0 | 3,042 | 0 | 0 | Financial Reports |
| Budget and Treasury | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | Financial Reports |
| Corporate Services | 3,519 | 375 | 28 | 3,519 | 375 | 28 | 3,519 | 375 | 28 | Financial Reports |
| Community and Social Services | 3,851 | 83 | 964 | 3,851 | 83 | 964 | 3,851 | 83 | 964 | Financial Reports |
| Public Safety | 1,005 | 50 | 218 | 1,005 | 50 | 218 | 1,005 | 50 | 218 | Financial Reports |
| Economic and Environmental Services | 1,425 | 0 | 0 | 1,425 | 0 | 0 | 1,425 | 0 | 0 | Financial Reports |
| Road Transport | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | Financial Reports |
| Electricity | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | Financial Reports |
| Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Water Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Management | 450 | 0 | 945 | 450 | 0 | 945 | 450 | 0 | 945 | Financial Reports |
| Total by Vote | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 |  |

Monthly Projections of Revenue and Expenditure by Vote: Fourth Quarter

| Expenditure and Revenue by Vote | April 2015 |  |  | May 2015 |  |  | June 2015 |  |  | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev |  |
| Executive and council | 3,042 | 0 | 0 | 3,042 | 0 | 0 | 3,042 | 0 | 0 | Financial Reports |
| Budget and Treasury | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | 7,288 | 0 | 19,305 | Financial Reports |
| Corporate Services | 3,519 | 375 | 28 | 3,519 | 375 | 28 | 3,519 | 375 | 28 | Financial Reports |
| Community and Social Services | 3,851 | 83 | 964 | 3,851 | 83 | 964 | 3,851 | 83 | 964 | Financial Reports |
| Public Safety | 1,005 | 50 | 218 | 1,005 | 50 | 218 | 1,005 | 50 | 218 | Financial Reports |
| Economic and Environmental Services | 1,425 | 0 | 0 | 1,425 | 0 | 0 | 1,425 | 0 | 0 | Financial Reports |
| Road Transport | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | 7,057 | 2,273 | 2,640 | Financial Reports |
| Electricity | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | 8,931 | 2,317 | 8,694 | Financial Reports |
| Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Water Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Reports |
| Waste Management | 450 | 0 | 945 | 450 | 0 | 945 | 450 | 0 | 945 | Financial Reports |
| Total by Vote | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 | 36,568 | 5,098 | 32,794 |  |

| Vote No. | Expenditure and Revenue by Vote | 2014/15 Total Expenditure and Revenue by Vote |  |  | Evidence Required |
| --- | --- | --- | --- | --- | --- |
|  |  | Opex | Capex | Rev |  |
|  | Executive and Council | 36,507 | 0 | 0 | Financial Reports |
|  | Budget and Treasury | 87,451 | 0 | 231,665 | Financial Reports |
|  | Corporate Services | 42,227 | 4,500 | 330 | Financial Reports |
|  | Community and Social Services | 46,217 | 1,000 | 11,565 | Financial Reports |
|  | Public Safety | 12,066 | 600 | 2,621 | Financial Reports |
|  | Economic and Environmental Services | 17,094 | 0 | 0 | Financial Reports |
|  | Road Transport | 84,682 | 27,279 | 31,685 | Financial Reports |
|  | Electricity | 107,174 | 27,800 | 104,327 | Financial Reports |
|  | Water | 0 | 0 | 0 | Financial Reports |
|  | Waste Water Management | 0 | 0 | 0 | Financial Reports |
|  | Waste Management | 5,174 | 0 | 11,337 | Financial Reports |
|  | Total by Vote | 438,819 | 61,179 | 393,530 |  |

Total Monthly Projections of Revenue and Expenditure by Vote for 2014/15

# KPA 1:

# MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT

| KPA 1: Municipal Transformation and Institutional Development 15% |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PMS No. & Performance Area | Cluster | IDP Objective | Key Performance Indicator | Unit of Measurement | Responsible Manager | Baseline (30/06/14) | Annual Target 30/06/15 | Budget | 2014/15 Quarterly Projections |  |  |  | Evidence Required |
|  |  |  |  |  |  |  |  |  | 1st Quarter (1 Jul – 30 Sept 14) | 2nd Quarter (1 Oct – 31 Dec 14) | 3rd Quarter (1 Jan – 31 Mar 15) | 4th Quarter (1 Apr – 30 Jun 15) |  |
| 1.1 Organisational Design & Human Resource |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Good governance and administration | Attract, develop and retain best human capital | Review of organisational structure | Deadline for Final Reviewed Organisational structure | Director Corporate Services | 30/06/2014 | 30/06/2015 |  | n/a | n/a | n/a | 30/06/15 | Reviewed organizational structure |
| 1.1.2 | Good governance and administration | Good corporate governance and public participation | Effective and up to date HR policies | # of HR policies reviewed and | Director Corporate Services | 6 policies reviewed | 8 policies |  | 2 policies Staff provisioning COIDA | 4 policies Relocation Probationary | 6 policies Retention Training and development | 8 policies Overtime Bereavement | Reviewed policies; council resolution |
| 1.1.3 | Good governance and administration | Attract, develop and retain best human capital | Reducing the vacancy rate | No. of vacant positions to be filled | Director Corporate Services | 20 positions filled | 20 Positions |  | 5 position | 10 positions | 15 position | 20 positions | Appointment letters; appointment register |
| 1.1.4 | Good governance and administration | Attract, develop and retain best human capital | Filling of all vacant S57 managers positions | # of section 57 positions to be filled | Director Corporate Services | - | 1position to be filled |  | n/a | 1 position | n/a | n/a | Appointment letters; appointment register |
| 1.2 Employment Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Good governance and administration | Good corporate governance and public participation | Implementation of Employment Equity Plan | No. of employees from previously disadvantaged groups appointed in the three highest levels of management as per EEP (PL 0,2,3) | Director Corporate Services |  | 2 positions to be filed. |  | n/a | n/a | n/a | 2 positions | Appointment letters; appointment register |
| 1.3 Skills Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Good governance and administration | Attract, develop and retain best human capital | Review and submission of Skills Development Plan | Deadline for reviewed and submission of Skills Development Plan | Director Corporate Services | 30/06/2014 | 30/04/2015 |  | n/a | n/a | n/a | 30/04/15 | WSP & proof of submission to LG SETA |
| 1.3.2 | Good governance and administration | Attract, develop and retain best human capital | Expenditure on implementation of municipal Workplace Skills Plan | 1% of municipal budget( salary budget) allocated for work place skills plan | Director Corporate Services | R1,5m | 1 500 |  | 375 | 750 | 1125 | 1500 | Expenditure reports; implementation reports |
| 1.4 Integrated Development Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Good governance and administration | Good corporate governance and public participation | Reviewed IDP/Budget/PMS/MPAC Framework and Process Plan | Deadline for approval of Process Plan by Council | Municipal Manager | 31/07/13 | 31/07/14 |  | 31/07/14 | n/a | n/a | n/a | Council Approved IDP, Budget, PMS Process Plan |
| 1.4.2 | Good governance and administration | Good corporate governance and public participation | Approval of Draft IDP | Deadline for approval of Draft IDP by Council | Municipal Manager | 31/03/14 | 31/04/15 |  | n/a | n/a | n/a | 31/04/15 | Council Approved Draft IDP/ Council Resolution |
| 1.4.3 | Good governance and administration | Good corporate governance and public participation | Approval of Final IDP | Deadline for approval of Final IDP by Council | Municipal Manager | 31/05/14 | 31/05/15 |  | n/a | n/a | n/a | 31/05/15 | Council Approved Final IDP/ Council resolution |
| 1.5 Performance Management System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Good governance and administration | Good corporate governance and public participation | Review of monthly performance by Senior Management | # of review meetings held per quarter | Municipal Manager | 11 | 11 |  | 3 | 5 | 8 | 11 | Minutes for senior management meetings, Attendance register |
| 1.5.2 | Good governance and administration | Good corporate governance and public participation | Review of monthly performance by portfolio committees | Total # of monthly portfolio committee meetings successfully held per quarter | Municipal Manager | 55 | 55 |  | 15 | 25 | 40 | 55 | Portfolio committee minutes, Attendance register |
| 1.5.3 | Good governance and administration | Good corporate governance and public participation | Signed performance agreements for all S57 Managers | Deadline for signed performance agreements | Municipal Manager | 01/07/13 | 10/07/14 |  | 10/07/14 | n/a | n/a | n/a | Copies of signed Performance Agreements & submission letters to CoGHSTA. |
| 1.5.4 | Good governance and administration | Good corporate governance and public participation | Submission of Institutional Annual Performance Report | Deadline for submission of Institutional Annual Performance Report | Municipal Manager | 31/08/13 | 31/08/14 |  | 31/08/14 | n/a | n/a | n/a | Council Approved Annual Performance Report |
| 1.5.5 | Good governance and administration | Good corporate governance and public participation | Tabling of Draft Annual Report to Council by the Mayor | Deadline for tabling Annual Report for 2013/14 | Municipal Manager | 31/01/14 | 31/01/15 |  | n/a | n/a | 31/01/15 | n/a | Council Approved 2012/13 Annual Report |
| 1.5.6 | Good governance and administration | Advance good corporate governance | Submission of Annual Report and Oversight Report on the 2013/14 Annual Report to Council by the MPAC | Deadline for submission of Oversight Report on the 2013/14 Annual Report | Municipal Manager | 31/03/13 | 31/03/14 |  | n/a | n/a | 31/03/15 | n/a | Dated proof of submission |
| 1.5.7 | Good governance and administration | Advance good corporate governance | Submission of Mid –Year report to stakeholders | Deadline for submission of Mid –Year report to stakeholders | Municipal Manager | 25/01/14 | 25/01/15 |  | n/a | n/a | 25/01/15 | n/a | Dated proof of submission |
| 1.5.8 | Good governance and administration | Good corporate governance and public participation | Approval of Draft SDBIP | Deadline for approval of Draft SDBIP by the Mayor | Municipal Manager | 20/03/14 | 20/03/15 |  | n/a | n/a | 20/03/15 | n/a | Signed & Approved Draft SDBIP for 2014/15 by the Mayor |
| 1.5.9 | Good governance and administration | Good corporate governance and public participation | Submission of Draft SDBIP to Council for noting | Deadline for Draft SDBIP submission to Council | Manager Municipal | 30/03/14 | 30/03/15 |  | n/a | n/a | 30/03/15 | n/a | Signed & Approved Draft SDBIP by the Mayor & Council Resolution |
| 1.5.10 | Good governance and administration | Good corporate governance and public participation | Approval of Final SDBIP | Deadline for approval of Final SDBIP by Mayor | Municipal Manager | 28/06/14 | 28/06/15 |  | n/a | n/a | n/a | 28/06/15 | Signed and Approved Final SDBIP by the Mayor |
| 1.5.11 | Good governance and administration | Good corporate governance and public participation | SDBIP Review | Deadline for reviewed Institutional SDBIP | Director Planning | 28/02/14 | 28/02/15 |  | n/a | n/a | 28/02/15 | n/a | Signed and Approved Reviewed 2014/15 SDBIP by the Mayor. |

# KPA 2:

# BASIC SERVICE DELIVERY

| KPA 2: Basic Service Delivery 25 % |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PMS No. & Performance Area | Cluster | IDP Objective | Key Performance Indicator | Unit of Measurement | Responsible Manager | Baseline (30/06/14) | Annual Target 30/06/15 | Budget | 2014/15 Quarterly Projections |  |  |  | Evidence Required |
|  |  |  |  |  |  |  |  |  | 1st Quarter (1 Jul – 30 Sept 14) | 2nd Quarter (1 Oct – 31 Dec 14) | 3rd Quarter 1 Jan – 31 Mar 15) | 4th Quarter (1 Apr – 30 Jun 15) |  |
| 2.1 Water Services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Improving water quality | % improvement on water quality level as per the blue drop standards | Director Technical Services | 80% | 90% |  | N/A | N/A | N/A | 90% | Assessment report by DWA |
| 2.2 Electricity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Provision of free basic electricity | # of indigent HH receiving free basic electricity | Chief Financial Officer | 4 000 HH | 4000 HH |  | 4000 HH | 4000 HH | 4000 HH | 4000 HH | Indigent register |
| 2.2.2 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | New electricity connections (Ba-Phalaborwa) | # of new consumer units connected to the electricity network | Director Technical Services | 600 | 652 |  | 163 | 326 | 489 | 652 | Project completion report |
| 2.2.3 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Provision of basic water supply | # of HH with access to basic water supply | Director Technical Services | 37468 | 41116 |  | Reporting Indicator |  |  |  |  |
| 2.2.4 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Provision of basic sanitation services | # of HH with access to sanitation service | Director Technical Services | 37468 | 41116 |  | Reporting Indicator |  |  |  |  |
| 2.2.5 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Provision of basic electricity services | # of HH with access to electricity | Director Technical Services | 39831 | 41116 |  | Reporting Indicator |  |  |  |  |
| 2.2.6 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Review of electricity maintenance plan | Deadline for reviewed electricity maintenance plan | Director Technical Services | 30/06/14 | 30/06/15 |  | n/a | n/a | 30/06/15 | n/a | Reviewed maintenance plan |
| 2.3 Waste Removal |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Households access to basic waste removal services (Phalaborwa, Namakgale, Lulekani & Gravelotte) | No. of households with access to refuse removal services | Director Community and Social Services | 22 941 | 22 941 |  | 22 941 | 22 941 | 22 941 | 22 941 | Monthly Report |
| 2.3.2 | Technical infrastructure | Sustain the environment | Implementing of land for landfill site | Deadline for implementation of landfill site | Director Planning & Development | Land acquired | 31/12/14 |  | n/a | Implementation 31/12/14 | n/a | n/a | Handover reports on established land fill site |
| 2.4 Roads & Storm Water |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Upgrading of gravel roads to paving /tar | # of km of gravel roads upgraded to paving / tar(B1 ext 1km, Tambo str 1.5km & Foskor str 2km) | Director Technical Services | 6km | 4.5 km | 22m | N/A | N/A | n/a | 4.5 km | Projects completion reports |
| 2.4.2 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Upgrading of gravel roads | # of km rehabilitated (Namakgal, Lulekani & Phalaborwa) | Director Technical Services | - | 2km | 5m | n/a | n/a | 1km | 2km | Projects completion reports |
| 2.4.3 | Technical infrastructure | Provision of sustainable integrated infrastructure and services | Capital expenditure on roads projects | R-value and % of roads capital funding spent | Director Technical Services | R21 040 000 | 20m | 22m | 6m | 10m | 14m | 220m | Payment Certificates |
| 2.5 Implementation of MIG Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Economic | Promotion of local economy | Implementation of capital projects through EPWP | # of Projects implemented EPWP way (B1 Ext, Foskor , Tambo, street Patamedi, Mashishimale, Namakgale Rehjabilitatio, PHB High mast, Selati Substation, Malungane electrification | Director Technical Services | 9 | 9 |  | 4 | 9 | n/a | n/a | EPWP Report |
| 2.6 Parks and Cemeteries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Technical infrastructure | Sustain the environment | Maintenance of recreational areas | Deadline for reviewed mowing and maintenance roster | Director Community and Social Services | 30/06/2014 | 30/06/2015 |  | n/a | n/a | n/a | 30/06/2015 | Schedule and Maintenance Report |
| 2.7 Human Settlements & Spatial Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Governance and Administration | Sustain the environment | Compliance and integration to SDF and LUMS | # of Land Use Management Reports | Director Planning & Development | 4 | 4 |  | 1 | 2 | 3 | 4 | Land Use Management Reports |
| 2.7.2 | Approval of municipal housing beneficiary list | Approval of municipal housing beneficiary list | Development of new municipal valuation roll | Deadline for development of new municipal valuation roll | Director Planning & Development | - | 30/06/15 |  | N/A | N/A | N/A | 30/06/15 | A new valuation roll |
| 2.8 MIG & INEG GRANTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.1 | Technical infrastructure | Integrate technical infrastructure and services for sustainability | Capital expenditure on projects | R-value of capital budget spent (MIG) | Director Technical Services | - | 29 767 000 |  | 8m | 16m | 24m | 29 767 000 | Expenditure report |
| 2.8.2 | Technical infrastructure | Integrate technical infrastructure and services for sustainability | Capital expenditure on electricity projects | R-value of electricity capital budget spent (INEG) | Director Technical Services | - | 9m |  | 3m | 6m | 9m | n/a | Expenditure report |

# KPA 3:

# LOCAL ECONOMIC DEVELOPMENT

| KPA 3: Local Economic Development 25% |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PMS No. & Performance Area | Cluster | IDP Objective | Key Performance Indicator | Unit of Measurement | Responsible Manager | Baseline (31/06/14) | Annual Target 30/06/15 | Budget | 2014/15 Quarterly Projections |  |  |  | Evidence Required |
|  |  |  |  |  |  |  |  |  | 1st Quarter (1 Jul – 30 Sept 14) | 2nd Quarter (1 Oct – 31 Dec 14) | 3rd Quarter (1 Jan – 31 Mar 15) | 4th Quarter 1 Apr – 30 Jun 15) |  |
| 3.1 Job Creation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Economic | Promotion of local economy | Creating jobs through municipal activities | Total # of jobs created through municipal activities | Municipal Manager | 560 | 600 |  | 150 | 300 | 450 | 600 | Job creation monthly reports |
| 3.1.2 | Economic | Promotion of local economy | Implementation of CWP Initiatives | # of CWP reports submitted to council | Director Planning & Development | - | 4 |  | 1 | 2 | 3 | 4 | Quarterly CWP reports |
| 3.2 Enterprise Support |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Economic | Promotion of local economy | SMME Support | # of SMMEs supported through procurement | Director Planning & Development | 80 | 120 |  | 40 | 80 | 100 | 120 | SMME Support Monthly reports |
| 3.2.2 | Economic | Promotion of local economy | Economic status quo report | # of status Quo reports in line with LED strategy | Director Planning & Development | - | 1 |  | n/a | n/a | n/a | 1 | Status Quo reports |
| 3.3 Tourism Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Economic | Promotion of local economy | # of municipal tourism development initiatives | # of municipal tourism development initiatives (Tourism Indaba, September Tourism month & Marula Festival) | Director Planning & Development | 3 | 3 |  | 1 | n/a | 2 | 3 | Quarterly reports on municipal tourism development initiatives |
| 3.4 Social Labour Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Economic | Promotion of local economy | Reports on the implementation of social labour plans | # of reports submitted to Management on the implementation of social labour plans | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Quarter reports on SLP Implementation |

# KPA 4:

# MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT

| KPA 4: Municipal Financial Viability and Management 20% |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PMS No. & Performance Area | Cluster | IDP Objective | Key Performance Indicator | Unit of Measurement | Responsible Manager | Baseline (30/06/14) | Annual Target 30/06/15 | Budget | 2014/15 Quarterly Projections |  |  |  | Evidence Required |
|  |  |  |  |  |  |  |  |  | 1st Quarter (1 Jul – 30 Sept 14) | 2nd Quarter (1 Oct – 31 Dec 14) | 3rd Q uarter (1 Jan – 31 Mar 15) | 4th Quarter 1 Apr – 30 Jun 15) |  |
| 4.1 Financial Viability |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Governance and administration | Improve financial viability | Operating Revenue | R-Operating Revenue | Chief Financial Officer | 334,540 | 393,530 |  | 98,383 | 196,765 | 295,148 | 393,530 | Finance reports |
| 4.1.2 | Governance and administration | Improve financial viability | Capital expenditure | R-value of capital budget spent | Chief Financial Officer | 60,620 | 61,179 |  | 15,295 | 30,590 | 45,884 | 61,179 | Finance reports |
| 4.2 Grant Expenditure and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Governance and administration | Improve financial viability | Monitoring expenditure on MSIG | R-value of total budget spent | Chief Financial Officer | 890 | 934 |  | 234 | 467 | 701 | 934 | Finance reports |
| 4.2.2 | Governance and administration | Improve financial viability | Monitoring expenditure on MIG | R-value of total budget spent | Chief Financial Officer | 24,333 | 29,767 |  | 7,442 | 14,884 | 22,325 | 29,767 | Finance reports |
| 4.2.3 | Governance and administration | Improve financial viability | Monitoring expenditure on operational conditional grants. | R-value of operational conditional grants spent FMG. | Chief Financial Officer | 1,550 | 1600 |  | 400 | 800 | 1,200 | 1,600 | Finance reports |
| 4.3 Financial Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Good governance and administration | Good corporate governance and public participation | Council approved budget planning schedule | Deadline for approved budget planning schedule | Chief Financial Officer | 31/08/2013 | 31/08/14 |  | 31/08/14 | N/A | N/A | N/A | approved budget planning schedule |
| 4.3.2 | Good governance and administration | Good corporate governance and public participation | Approval of Draft Budget | Date of approval of Draft Budget by Council | Municipal Manager | 31/03/2014 | 31/03/15 |  | n/a | n/a | 31/03/15 | n/a | Draft Budget by Council |
| 4.3.3 | Good governance and administration | Good corporate governance and public participation | Approval of Final Budget | Date of approval of Final Budget by Council | Municipal Manager | 31/05/2014 | 31/05/2015 |  | N/A | N/A | N/A | 31/05/2015 | Final Budget by Council |
| 4.3.4 | Good governance and administration | Good corporate governance and public participation | Approval of adjustments budget | Deadline for approving adjustments budget | Municipal Manager | 28/02/2014 | 28/02/2015 |  | N/A | N/A | 28/02/2015 | N/A | Adjustment budget document; council resolution |
| 4.3.5 | Good governance and administration | Good corporate governance and public participation | Review of budget policies | Deadline for review of budget related policies | Municipal Manager | 31/03/2014 | 31/03/15 |  | N/A | N/A | 31/03/15 | N/A | Approved budget related policies |
| 4.3.6 | Good governance and administration | Good corporate governance and public participation | Appointment of Supply Chain structures / Committees members in writing | Deadline for Appointment of Supply Chain structures / Committees members | Municipal Manager | 31/06/2013 | 07/07/2014 |  | 07/07/2014 | N/A | N/A | N/A | Appointment letters of bid committees members |
| 4.3.7 | Governance and administration | Improve financial viability | Asset management | # asset verifications and maintenance conducted | Chief Financial Officer | 4 | 4 |  | 1 | 2 | 3 | 4 | Quarterly Assets verifications reports |
| 4.3.8 | Governance and administration | Improve financial viability | Oversight on quarterly financial reports (Revenue, Expenditure, Assets & SCM) | # of oversight reports | Municipal Manager | 4 | 4 |  | 2 | 2 | 3 | 4 | Quarterly Audit Committee Report |
| 4.3.9 | Good governance and administration | Good corporate governance and public participation | Review of five year financial plan | Deadline for reviewed five year financial plan | Chief Financial Officer | 31/03/2014 | 31/03/15 |  | N/A | N/A | 31/03/15 | N/A | Approved financial plan |
| 4.3.10 | Governance and administration | Improve financial viability | Implementation of revenue enhancement strategy | # of implementation reports compiled | Chief Financial Officer | 4 | 4 |  | 1 | 2 | 3 | 4 | Quarterly reports on revenue enhancement |
| 4.3.11 | Governance and administration | Improve financial viability | Improved revenue collection | % improvement in revenue collection | Municipal Manager | 80% | 65% |  | 20% | 30% | 45% | 65% | Quarterly reports on revenue collection |
| 4.3.12 | Good governance and administration | Good corporate governance and public participation | Updated indigent register for the provision of free basic services | Deadline for updated indigent register | Chief Financial Officer | 30/06/2014 | 30/06/2015 |  | N/A | N/A | N/A | 30/06/2015 | Updated indigent register |
| 4.3.13 | Good governance and administration | Good corporate governance and public participation | Preparation of annual financial statements | Deadline for submission of annual financial statements to relevant stakeholders | Chief Financial Officer | 31/08/2013 | 31/08/2014 |  | 31/08/2014 | N/A | N/A | N/A | Completed AFS |
| 4.3.14 | Good governance and administration | Good corporate governance and public participation | Review of financial statements | # of reports on the review of Annual/Quarterly financial statements | Municipal Manager | 5 | 5 |  | 2 | 3 | 4 | 5 | Quarterly financial statements |
| 4.3.15 | Good governance and administration | Advance good corporate governance | Compliance with legislation (MFMA) | # of compliance/ financial reports submitted to Treasuries and CoGHSTA | Chief Financial Officer | 12 | 12 |  | 3 | 6 | 9 | 12 | Proof of submission |
| 4.3.16 | Good governance and administration | Advance good corporate governance | Compliance with legislation (MFMA) | Deadline of submission Monthly Sec 71 Reports to Stakeholders | Chief Financial Officer | 12 | Within 10 working days on a monthly basis |  | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Monthly Dated proof of submission |
| 4.3.17 | Good governance and administration | Advance good corporate governance | Compliance to Water Service Level Agreement | Monthly submission of reports, Submission of Invoices and Payment of Debt | Chief Financial Officer | - | Within 10 working days on a monthly basis |  | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Within 10 working days on a monthly basis | Monthly reports, submitted to MDM , Invoices & proof of payments to |

# KPA 5:

# GOOD GOVERNANCE & PUBLIC PARTICIPATION

| KPA 5: Good Governance and Public Participation 15% |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PMS No. & Performance Area | Cluster | IDP Objective | Key Performance Indicator | Unit of Measurement | Responsible Manager | Baseline (30/06/14) | Annual Target 30/06/15 | Budget | 2014/15 Quarterly Projections |  |  |  | Evidence Required |
|  |  |  |  |  |  |  |  |  | 1st Quarter (1 Jul – 30 Sept 14 ) | 2nd Quarter 1 Oct – 31 Dec 14) | 3rd Quarter 1 Jan – 31 Mar 15) | 4th Quarter (1 Apr – 30 Jun 15) |  |
| 5. 1 Council and Executive Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1.1 | Good governance and administration | Good corporate governance and public participation | Effective functioning of Council | # of scheduled Council meetings held | Director Corporate Services | 6 | 6 |  | 2 | 3 | 5 | 6 | Minutes of council meetings, attendance registers |
| 5.1.2 | Good governance and administration | Good corporate governance and public participation | Effective functioning of the Executive Committee | # of scheduled Exco meetings held | Director Corporate Services | 11 | 11 |  | 3 | 5 | 8 | 11 | Minutes of EXCO meetings, attendance registers |
| 5.1.3 | Good governance and administration | Good corporate governance and public participation | Effective functioning of MPAC | # of scheduled MPAC meetings held | Municipal Manager | 8 | 4 |  | 1 | 2 | 3 | 4 | Council Approved MPAC schedule of meetings/Attendance registers |
| 5.2 Public Participation and Ward Committees |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2.1 | Good governance and administration | Good corporate governance and public participation | Public involvement in IDP review process | # of IDP REP Forum meetings held | Municipal Manager | 6 | 6 |  | 2 | 2 | 5 | 6 | Attendance registers, agendas, invitations |
| 5.2.2 | Good governance and administration | Good corporate governance and public participation | Public involvement in IDP review process | # of IDP Steering Committee meetings held | Municipal Manager | 6 | 6 |  | 2 | 2 | 5 | 6 | Attendance registers, agendas, invitations |
| 5.2.3 | Good governance and administration | Good corporate governance and public participation | Public involvement in IDP review process | # of IDP Technical meetings held | Municipal Manager | 6 | 6 |  | 2 | 2 | 5 | 6 | Attendance registers, agendas, invitations |
| 5.2.4 | Good governance and administration | Good corporate governance and public participation | Effective functioning of ward committees | Number of ward reports generated | Municipal Manager | 11 | 11 |  | 3 | 5 | 8 | 11 | Consolidated Batho-Pele Reports |
| 5.2.5 | Good governance and administration | Good corporate governance and public participation | Making public the Annual Report and Oversight Report | Deadline for making public the Annual Report and the Oversight Report | Municipal Manager | 07/04/2014 | 07/04/2015 |  | n/a | n/a | n/a | 07/04/15 | Copy of the newspaper notice |
| 5.2.6 | Good governance and administration | Good corporate governance and public participation | Mayoral Imbizos | # of Mayoral Imbizos held | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Attendance registers, Imbizo reports |
| 5.3 Corporate Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3.1 | Good governance and administration | Good corporate governance and public participation | Development of Communication strategy | Deadline for developing Communication strategy as per GCIS guidelines | Municipal Manager | - | 30/06/2015 |  | n/a | n/a | n/a | 30/06/15 | Approved communication strategy |
| 5.3.2 | Good governance and administration | Good corporate governance and public participation | Review of system of delegation of powers | Deadline for reviewed delegation of powers | Municipal Manager | 30/06/2014 | 30/06/15 |  | n/a | n/a | n/a | 30/06/15 | Reviewed delegations of powers |
| 5.3.3 | Good governance and administration | Good corporate governance and public participation | Review code of conduct for staff members | Deadline for reviewed code of conduct | Director Corporate Services | 30/06/2014 | 30/06/2015 |  | n/a | n/a | n/a | 30/06/2015 | Reviewed code of conduct |
| 5.3.4 | Good governance and administration | Good corporate governance and public participation | Functional Performance Audit Committee | # of Performance Audit Committee meetings held | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Copies of minutes, attendance registers |
| 5.3.5 | Good governance and administration | Good corporate governance and public participation | Functional Performance Audit Committee | # of Audit Committee meetings held | Municipal Manager | 7 | 7 |  | 2 | 4 | 5 | 7 | Copies of minutes, attendance registers |
| 5.3.6 | Good governance and administration | Good corporate governance and public participation | Functional Internal Audit Unit | Deadline for approved Risk-based Audit Plan | Municipal Manager | 30/06/2014 | 30/06/15 |  | n/a | n/a | n/a | 30/06/15 | Approved Risk-based audit plan |
| 5.3.7 | Good governance and administration | Good corporate governance and public participation | Community satisfaction survey conducted | Deadline for a community satisfaction survey report | Director Planning & Development | 25/09/13 | 25/09/14 |  | 25/09/14 | n/a | n/a | n/a | Community Satisfaction Survey Report |
| 5.3.8 | Good governance and administration | Good corporate governance and public participation | Submission of Annual Financial Statements and Annual Performance Report | Deadline for submitting unaudited annual financial Statements and Annual Performance Report | Municipal Manager | 31/08/13 | 31/08/14 |  | 31/08/14 | n/a | n/a | n/a | Submission letter and copy of final AFS |
| 5.3.9 | Good governance and administration | Good corporate governance and public participation | Approved creditors payment procedure manual | Deadline for reviewed, documented approved internal controls | Chief Financial Officer | 30/06/2014 | 30/06/2015 |  | n/a | n/a | n/a | 30/06/2015 | Approved copy of internal controls |
| 5.3.10 | Good governance and administration | Good corporate governance and public participation | Audit Action Plan to address issues raised in the AG’s audit report | Deadline for adopting Audit Action Plan | Municipal Manager | 31/01/2014 | 31/01/15 |  | n/a | n/a | 31/01/15 | n/a | Approved audit action plan |
| 5.3.11 | Good governance and administration | Good corporate governance and public participation | Addressing audit queries (2012/13 Audit Report) | % of audit queries addressed | Municipal Manager | 75% | 100% |  | 100% | 100% | n/a | n/a | Audited AG Action Plan |
| 5.3.12 | Good governance and administration | Good corporate governance and public participation | Addressing audit queries (2013/14 Audit Report) | % of audit queries addressed | Municipal Manager | 75% | 80% |  | n/a | n/a | 50% | 80% | Audited AG Action Plan |
| 5.3.13 | Good governance and administration | Good corporate governance and public participation | Achieving clean by 2014 | Final Audit Report | Municipal Manager | Disclaimer | Qualified |  | n/a | Qualified | n/a | n/a | Audit Report |
| 5.3.14 | Good governance and administration | Good corporate governance and public participation | Implementation of internal audit recommendations | % of internal audit recommendations implemented | Municipal Manager & All Directors | 75% | 75% |  | 100% | 100% | 100% | 100% | IA Follow-up reports |
| 5.3.15 | Good governance and administration | Good corporate governance and public participation | Functionality of Audit Committee | # of Audit Committee Reports presented to Council | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Quarterly audit committee reports |
| 5.3.16 | Good governance and administration | Good corporate governance and public participation | Development of contract management system | Deadline for development of contract management system | Chief Financial Officer | 30/09/13 | 30/09/14 |  | 30/09/14 | n/a | n/a | n/a | Council Approved Contract management System |
| 5.3.17 | Good governance and administration | Good corporate governance and public participation | Functionality of Local Labour Forum (LLF) | # of LLF meetings held | Director Corporate Services | 11 | 11 |  | 3 | 5 | 8 | 11 | Minutes of LLF, Attendance registers |
| 5.3.18 | Good governance and administration | Good corporate governance and public participation | Functionality of Risk Management Committee | # of meetings held | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Minutes of risk committee meetings, Attendance registers |
| 5.4 Fraud & Anti Corruption Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4.1 | Good governance and administration | Good corporate governance and public participation | Reviewed fraud and anti-corruption strategy | Deadline for reviewed strategy | Municipal Manager | 30/06/2014 | 30/06/15 |  | n/a | n/a | n/a | 30/06/15 | Approved fraud and anti corruption policy |
| 5.5 Information Technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5.1 | Good governance and administration | Good corporate governance and public participation | Development of a municipal ICT strategy | Deadline for approved ICT Strategy | Director Corporate Services | 30/3/2014 | 30/06/15 |  | n/a | n/a | n/a | 30/6/2015 | Approved ICT strategy |
| 5.6 HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.6.1 | Good governance and administration | Provision of sustainable integrated infrastructure and services | Conducting outreach programmes | # of outreach programmes conducted | Director Community & Social Services | 4 | 16 |  | 4 | 8 | 12 | 16 | Outreach programmes reports |
| 5.7 Security management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.7.1 | Governance and Administration | Good corporate governance and public participation | Safeguarding of Council Assets | # of Security Management reports | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Security Management Reports |
| 5.7.2 | Governance and Administration | Good corporate governance and public participation | Updated Strategic Risk Register | Deadline for the approval of the Strategic Risk Register by Council | Municipal Manager | 30/06/2014 | 30/06/2015 |  | n/a | n/a | n/a | 30/06/15 | Council Approved Strategic Risk Register |
| 5.8 Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.8.1 | Governance and Administration | Good corporate governance and public participation | Functionality of a disaster management forum | # of disaster management forum meetings held | Municipal Manager | 4 | 4 |  | 1 | 2 | 3 | 4 | Agenda, attendance registers |

# CAPITAL WORKS PLAN

Capital Works Plan per Ward for 2014/15 – 2016/17

| Ward | Project No. | Project Name | Project Description | Planned Start Date | Planned Completion Date | Responsible Senior Manager | Capital Cost (R‘000) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 2014/15 | 2015/2016 |  | 2016/2017 |
| Traffic & Licensing |  |  |  |  |  |  |  |  |  |  |
|  | Com1 | New Drivers Licence test and exchange facility Phase 1 | New Drivers Licence test and exchange facility Phase 1: Final plans, fencing and start of construction | 01/07/14 | 30/06/15 | Director Community Services | 1m |  |  |  |
|  | Com 2 | Patrol/Traffic vehicles | Procurement of additional two functional Patrol/Traffic vehicles fully fitted and operationally ready (Phase 1) | 01/07/14 | 30/06/15 | Director Community | R600 |  |  |  |
| Electricity |  |  |  |  |  |  |  |  |  |  |
|  | Tech 1 | Construction of New 33KV switching room and switch gear at Selati | Construction of New 33KV switching room and switch gear at Selati | 01/07/14 | 31/01/15 | Director Technical | R8m |  |  |  |
|  | Tech 2 | Purchase of Cable locater unit panel van | Refurbishment of electricity infrastructure | 01/07/14 | 30/06/15 | Director Technical | R 1m |  |  |  |
|  | Tech 3 | Upgrade of 11kV medium voltage cable network in Ba-Phalaborwa town (Phase 1) | Refurbishment of electricity infrastructure Phalaborwa | 01/07/14 | 30/06/15 | Director Technical | R 1,8m |  | R 4m | R 4m |
| Roads & Storm water |  |  |  |  |  |  |  |  |  |  |
|  | Tech 4 | Rehabilitation of streets in Phalaborwa (Gerdelandstr,Selati to Haarlem str and Park str) | Roads and storm water Phalaborwa, Namakgale & Lulekani | 01/07/14 | 30/06/15 | Director Technical | R 5m |  | R 5m | R 5m |
|  | Tech 6 | storm water culverts around Ba-Phalaborwa Municipality(Maseke Ward 10,Makhushane ward2 and ) | Construction of storm water culverts around Ba-Phalaborwa Municipality(Maseke Ward 10,Makhushane ward2 and Kanana) | 01/07/14 | 30/06/15 | Director Technical | R 1.5m |  | R 1.5m | R 1.5m |
|  | Tech 6 | Extension of Municipal Offices Phase 2(Design) | Extension of Municipal Offices Phase 2(Design) | 01/07/14 | 30/06/15 | Director Technical | R 0.5m |  | R 4m | R 4m |
| Corporate , Information & Communication Technology |  |  |  |  |  |  |  |  |  |  |
|  | Corp 1 | Office Furniture &Equipments | Office Furniture &Equipments | 01/07/14 | 30/06/15 | Director Corporate | R1,5m |  |  |  |
|  | Corp 2 | Centralised Archived Lulekani (Finalization) | Centralised Archived Lulekani (Finalization) | 01/07/14 | 30/06/15 | Director Corporate | R1m |  |  |  |
|  | Corp 3 | ICT infrastructure | Software/Hardware equipments | 01/07/14 | 30/06/15 | Director Corporate | R2m |  |  |  |
| MIG Projects |  |  |  |  |  |  |  |  |  |  |
|  | MIG1 | Tambo street paving | Tambo street paving | 01/07/14 | 30/06/15 | Director Technical | R 6m |  | R 7m | N/A |
|  | MIG 2 | Upgrading of internal street at Foskor (Namakgale township) | Upgrading of internal street at Foskor (Namakgale township) | 01/07/14 | 30/06/15 | Director Technical | R 4m |  | R10m | R12m |
|  | MIG3 | Upgrading of B1 extension road | Upgrading of B1 extension road | 01/07/14 | 30/06/15 | Director Technical | R 3m |  | R 5m |  |
|  | MIG4 | Mashishimalemulti sport complex | Mashishimale multi sport complex | 01/07/14 | 30/06/15 | Director Technical | R 4m |  | R4m |  |
|  | MIG5 | Patamedi street paving | Patamedi street paving | 01/07/14 | 31/07/14 | Director Technical | R 1.7m |  |  |  |
|  | MIG6 | Ba-Phalaborwa energy saving highmast(Phase 2 Maseke,Mashishimale R 1,2,3 and Phase 1 Makhushane | Ba-Phalaborwa energy saving highmast(Phase 2 Maseke,Mashishimale R 1,2,3 and Phase 1 Makhushane | 01/07/14 | 30/06/15 | Director Technical | R 8m |  | R 7m |  |
|  | MIG7 | Honiville to Topville street paving | Honiville to Topville street paving | 01/07/14 | 31/07/14 | Director Technical | R 1m |  | N/A | N/A |
|  | MIG8 | Selwane street paving Phase 1 | Selwane street paving Phase 1 | 01/07/14 | 31/07/14 | Director Technical | R 1m |  | N/A | N/A |
| INEG |  |  |  |  |  |  |  |  |  |  |
|  | INEG 1 | Electrification of Malungane, Nyakelang and Tshube |  | 01/07/14 | 30/11/14 | Director Technical | R 9m |  | N/A | N/A |

# CAPITAL PROJECTS PER RESPONSIBLE MANAGER

# Summary of Capital Projects per Responsible Manager by Vote

| Vote No. | Responsible Manager | Project Name |  | Total Capital Budget (R’000) | Planned Start Date | Planned Completion Date | Ward No. | Quarterly Outputs 2014/15 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | 1st Quarter 01 Jul - 30 Sept 2014 | 2nd Quarter 01 Oct - 31 Dec 2014 | 3rd Quarter 01 Jan – 31 Mar 2015 | 4th Quarter 01 Apr – 30 Jun 2015 |  |  | Evidence required |  |  |
| Traffic & Licensing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Community | New Drivers Licence test and exchange facility Phase |  | 1m | 01/07/2014 | 30/06/15 |  | n/a | Identification of land | EIA and Procurement | Re-zoning completed if required |  |  | Payment Certificates |  |  |
|  | Director Community | Procurement of additional two functional Patrol/Traffic vehicles fully fitted and operationally ready (Phase 1) |  | 600 | 01/07/14 | 30/06/15 |  | Specification Committee appointed. Requisition submitted | Tender adjudication goods delivered | n/a | n/a |  |  | Payment Certificates |  |  |
| Electricity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Technical | Construction of New 33KV switching room and switch gear at Selati |  | R8m | 01/07/2014 | 31/01/15 | 11 | 2.6m | 5,2.m | 8m |  |  |  | Progress report and payment certificate |  |  |
|  | Director Technical | Purchase of Cable locater unit panel van |  | R1m | 01/07/2014 | 30/09/14 | 11 | 1m | N/A | N/A | N/A |  |  | Progress report and payment certificate |  |  |
|  | Director Technical | Upgrade of 11kV medium voltage cable network in Ba-Phalaborwa town (Phase 1) |  | R 1.8.m | 01/07/2014 | 30/06/15 | 12 | .8m | .8m | N/A |  |  |  | Progress report and payment certificate |  |  |
|  |  |  | Roads & Storm water |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Technical | Rehabilitation of streets in Phalaborwa (Gerdelandstr,Selati to Haarlem str and Park street , Namakgale & Lulekani) |  | R5m | 01/07/2014 | 30/06/15 | 12 | 1.25m | 2,5m | 3.75m | 5m |  | Progress report and payment certificate |  |  |  |
|  | Director Technical | Construction of storm water culverts around Ba-Phalaborwa Municipality(Maseke Ward 10,Makhushane ward2 and Kanana ) |  | R1,5M | 01/07/2014 | 30/06/15 | 10 & 2 | 0-375m | 0-750m | 0-1100m | 0-1500m |  | Progress report and payment certificate |  |  |  |
|  | Director Technical | Extension of municipal offices phase 2 (Design) |  | 500 | 01/07/14 | 30/06/15 | 12 | 200 | 350 | 500 | n/a |  | Payments certificates |  |  |  |
| Corporate, Information & Communication Technology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Corporate | Office Furniture &Equipments |  | R1.5m | 01/07/14 | 30/6/2015 |  | 375 | 750 | 1100 | 1500 | Payments certificates |  |  |  |  |
|  | Director Corporate | Centralised Archived Lulekani (Finalization) |  | R1m | 01/07/14 | 30/6/2015 |  | 250 | 500 | 750 | 1 000 | Payments certificates |  |  |  |  |
|  | Director Corporate | ICT Infrastructure &equipment upgrades |  | R2m | 01/07/14 | 30/6/2015 |  | 500 | 1,000 | 1,500 | 2,000 | Payments certificates |  |  |  |  |
| MIG Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Technical | Tambo street paving |  | R6 m | 01/07/14 | 30/06/15 | 7 | 0.6m | 2,6 m | 4,6 m | 6m | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Upgrading of internal street at Foskor (Namakgale township) |  | R4m | 01/07/14 | 30/06/15 |  | 0.4m | 1.6m | 3m | 4m | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Upgrading of B1 extension road |  | R3m | 01/07/14 | 30/06/15 | 15 | 0.3m | 1,3m | 2,3m | 3m | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Mashishimalemulti sport complex |  | R4m | 01/07/14 | 30/06/15 | 8 | 0.4m | 1.6m | 3m | 4m | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Patamedi street paving |  | R1.7m | 01/07/14 | 31/07/14 | 9 | 1.7m | n/a | n/a | n/a | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Ba-Phalaborwa energy saving highmast(Phase 2 Maseke,Mashishimale R 1,2,3 and Phase 1 Makhushane |  | R8m | 01/07/14 | 30/06/15 | 10 8 9 | 2m | 4m | 6m | 8m | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Honiville to Topville street paving |  | R 1.m | 01/07/14 | 31/07/14 | 1 | 1m | n/a | n/a | n/a | Progress report and payment certificate |  |  |  |  |
|  | Director Technical | Selwane street paving Phase 1 |  | R 1.m | 01/07/14 | 31/07/14 | 18 | 1m | n/a | n/a | n/a | Progress report and payment certificate |  |  |  |  |
| INEG Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Director Technical | Electrification of Malungane, Nyakelang and Tshube |  | 9m | 01/07/14 | 30 | 4 | 4.5m | 9m | n/a | n/a | Progress report and payment certificate |  |  |  |  |

# SDBIP APPROVAL

| Approval by the Mayor | This SDBIP is a management and implementation plan (and not a policy proposal) and is therefore not required to be approved by the Council. The approval of the SDBIP is a competency reserved for the Municipal Manager and the Mayor of the Municipality in terms of Section 53 of the MFMA. The Municipal Manager becomes responsible for ensuring that the SDBIP is submitted to the Mayor within 14 days of approval of the adjusted SDBIP and the Budget and approved within 28 days of the approval of the IDP and Budget. |
| --- | --- |
| Monitoring implementation of the SDBIP | Progress against the objectives set out in the SDBIP will be monitored and reported on a monthly, quarterly, half-yearly and annual basis. |
| Signatures | SDBIP Compiled by: ------------------------------------------- ----------------------------------- Dr. SS Sebashe Date Municipal Manager SDBIP Approved By: ----------------------------------------- ----------------------------------- Cllr SONO NA Date Mayor |